{"text_format":"2","workbook":"xls","n_sheets":7,"sheets":["Kopā","Savilkums","1","2","3","4","5"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Kopā","index":0,"n_rows":21,"n_cols":5,"rows_kept":21,"cut":false,"hidden":false,"merged":[[7,0,7,4],[15,2,16,3],[17,2,17,3],[17,0,17,1],[15,0,16,1],[15,4,16,4]],"flags":["formulas_cached_only"]}
[null,null,"APSTIPRINU:"]
[]
[{"$nulls":4},"/______________/___________________/"]
[null,null,null,"             Paraksts                             atšifrējums"]
[{"$nulls":4},"z.v."]
[{"$nulls":4},"2011. g. \"_____  \"________________"]
[]
["Būvniecības koptāme"]
["Būves nosaukums:",null,"Kolkas pamatskola"]
["Objekta nosaukums:",null,"Kolkas pamatskolas 1. stāva remonts"]
["Objekta adrese:",null,"Kolkas pamatskola, Kolka, Kolkas pagasts, Dundagas novads, LV - 3275"]
["Pasūtījuma Nr.",null,"Dundagas novada pašvaldība"]
[]
[null,null,"Cilvēkstundas: ",null,0]
[null,null,"Tāme sastādīta:",null,0]
["Tāmes nr.",null,"Tāmes nosaukums",null,"Izmaksas BEZ PVN 22% Ls"]
[]
["1",null,"Kolkas pamatskolas 1. stāva remonts",null,0]
[null,null,null,"Kopā bez PVN Ls:",0]
[null,null,null,"PVN 22% Ls:",0]
[null,null,null,"Kopā ar PVN Ls:",0]

{"sheet":"Savilkums","index":1,"n_rows":28,"n_cols":8,"rows_kept":28,"cut":false,"hidden":false,"merged":[[18,0,18,1],[19,0,19,1],[20,0,20,1],[14,4,15,4],[14,5,14,7],[6,0,6,7],[16,0,16,1],[14,0,15,1],[14,2,15,2],[14,3,15,3],[17,0,17,1]],"flags":["formulas_cached_only"]}
[{"$nulls":5},"APSTIPRINU:"]
[]
[{"$nulls":5},"/______________/___________________/"]
[{"$nulls":5},"     Paraksts                             atšifrējums"]
[{"$nulls":7},"z.v."]
[{"$nulls":5},"2011. g.","\"_____  \"________________"]
["Kopsavilkums"]
["Būves nosaukums:",null,"Kolkas pamatskola"]
["Objekta nosaukums:",null,"Kolkas pamatskolas 1. stāva remonts"]
["Objekta adrese:",null,"Kolkas pamatskola, Kolka, Kolkas pagasts, Dundagas novads, LV - 3275"]
["Pasūtījuma Nr.",null,"Dundagas novada pašvaldība"]
[]
[null,null,"Cilvēkstundas: ",0]
[null,null,"Tāme sastādīta:"]
["Tāmes nr.",null,"Tāmes nosaukums","Tiešās izmaksas BEZ PVN 22% Ls","Darba ietilpība C/st","Kopējās izmaksas, tai skaitā"]
[{"$nulls":5},"Dalba alga Ls","Materiāli Ls","Mehanismi Ls"]
["1",null,"Remonta darbi telpā Nr.3 (dziedāšanas klase)",0,0,0,0,0]
[2,null,"Remonta darbi telpā Nr.4 (dežuranta ofiss, pirms tam kambaris pie dziedāšanas klases)",0,0,0,0,0]
[3,null,"Gaiteņa un garderobes nodalījumu remonts",0,0,0,0,0]
[4,null,"Durvju maiņa gaitenī",0,0,0,0,0]
[5,null,"Santehnikas darbi",0,0,0,0,0]
[null,null,"Tiešās izmaksas kopā Ls:",0,0,0,0,0]
[null,null,"Materiālu sagāde, transports ...% Ls:"]
[null,null,"Uzņēmuma virsizdevumi ...% Ls:"]
[null,null,"Plānotie uzkrājumi ...% Ls:"]
[null,null,"Neparedzētie izdevumi 5% Ls:"]
[null,null,"Darba devēja sociālais nodoklis 24.09% Ls:",0]
[null,null,"Kopā bez PVN 22% Ls:",0]

{"sheet":"1","index":2,"n_rows":79,"n_cols":17,"rows_kept":79,"cut":false,"hidden":false,"merged":[[76,0,76,4],[9,7,9,10],[9,16,12,16],[10,7,10,10],[9,12,9,15],[10,12,10,15],[0,0,0,15],[1,0,1,15],[7,11,7,12],[8,0,8,2],[8,11,8,12],[6,11,6,12]],"flags":["formulas_cached_only"]}
["Lokālā tāme Nr. 1"]
["Remonta darbi telpā Nr.3 (dziedāšanas klase)",{"$nulls":15},"Remonta darbi telpā Nr.3 (dziedāšanas klase)"]
["Būves nosaukums:",null,"Kolkas pamatskola"]
["Objekta nosaukums:",null,"Kolkas pamatskolas 1. stāva remonts"]
["Objekta adrese:",null,"Kolkas pamatskola, Kolka, Kolkas pagasts, Dundagas novads, LV - 3275"]
["Pasūtījuma Nr.",null,"Dundagas novada pašvaldība"]
[{"$nulls":10},"Cilvēkstundas: ",0]
[{"$nulls":10},"Tāme sastādīta:",0]
[{"$nulls":10},"Tiešās izmaksas:",0]
[{"$nulls":7},"Vienības izmaksa",{"$nulls":4},"Kopējās izmaksas"]
["Nr.","Normat.","Darba un izdevumu nosaukums","Vienība","Daudz.","Laika","Darba ","tai skaitā",null,null,null,"Darba","tai skaitā"]
["p.","pozic.","pielietotie materiāli, to daudzums",null,null,"norma","samaksa","Darba alga","Materiāli","Mehanismi","Kopā","ietilpība","Darba alga","Materiāli","Mehanismi","Kopā"]
["k.","nr.",null,null,null,"C/st","Ls","Ls","Ls","Ls","Ls","C/st","Ls","Ls","Ls","Ls"]
[1,2,3,4,5,6,7,"8","9","10","11","12","13","14","15","16"]
[null,null,"1. Demontāžas darbi"]
[1,null," Iekšdurvju demontāžas darbi","gab.",3,null,null,0,null,0,0,0,0,0,0,0]
[2,null,"Starpsienu demontāža","m2",38.5,null,null,0,null,0,0,0,0,0,0,0]
[3,null,"Grīdas seguma  demontāža ","m2",41.9,null,null,0,null,0,0,0,0,0,0,0]
[4,null,"Grīdas seguma konstrukcijas demontāža","m2",41.9,null,null,0,null,0,0,0,0,0,0,0]
[5,null,"Būvgružu nodošana izgāztuvē","t",5.2,null,null,0,null,0,0,0,0,0,0,0]
[6,null,"2. Sienas."]
[7,null,"Starpsienu metāla karkasa iebūve W112(100) riģipša plātne 2 kārtās","m²",32.65,null,null,0,null,0,0,0,0,0,0,0]
[8,null,"UW profils 100x40x06","m",0.74]
[9,null,"CW profils 100x50x06","m",2.06]
[10,null,"Dībelis K6/35","gb.",1.65]
[11,null,"Izolācijas plāksne Paroc UNS 100mm","m²",1.02]
[12,null,"Riģipša plāksne GKB","m²",4.1]
[13,null,"Riģipša skrūves TN25","100gb",0.132]
[14,null,"Riģipša skrūves TN35","100gb",0.295]
[15,null,"Riģipša virsmu sagatavošana krāsošanai","m²",26.4,null,null,0,null,0,0,0,0,0,0,0]
[16,null,"Šuvju lenta","m",1.58]
[17,null,"Špaktele Knuaf Uniflot","kg",5.28]
[18,null,"Veco sienu virsmu sagatavošana krāsošanai (tīrīšana, špaktelēšana, slīpēšana)","m²",78.3,null,null,0,null,0,0,0,0,0,0,0]
[19,null,"Špaktele Caparol Glattchtel","m²",1.03]
[20,null,"Sienu virsmu krāsošanas darbi","100m²",1.05,null,null,0,null,0,0,0,0,0,0,0]
[21,null,"Grunts Uni primer","l",12.5]
[22,null,"Krāsa sienām tonēta","l",25]
[23,null,"3. Ailu aizpildījums."]
[24,null,"PVC divviru durvju bloka montāža","gab.",1,null,null,0,null,0,0,0,0,0,0,0]
[25,null,"PVC durvju bloks 2000x2100","gab.",1]
[26,null,"Montāžas putas","bal",1]
[27,null,"Skrūves, dībeļi","kpl",6]
[28,null,"Stiprinājumi","gab.",6]
[29,null,"Iekšdurvju, koka 80x209cm iebūve","gab.",1,null,null,0,null,0,0,0,0,0,0,0]
[30,null,"Iekšdurvju bloks ","gab.",1]
[31,null,"Montāžas putas","balons",0.3]
[32,null,"Rokturi","gab.",1]
[33,null,"Seglīstes","m",5.6]
[34,null,"Skrūves, dībeļi","gab.",6]
[35,null,"Stiprinājumi","gab.",6]
[36,null,"4. Grīdas."]
[37,null,"Vājbetona sagatavošanas kārta b=100mm","m³",4.8,null,null,0,null,0,0,0,0,0,0,0]
[38,null,"Betons B5","m3",1.05]
[39,null,"Grīdas siltumizolācija b=100mm 1.stāva grīdām","m2",47.7,null,null,0,null,0,0,0,0,0,0,0]
[40,null,"Tenapors EPS100 100mm","m²",1.02]
[41,null," Javas M200 stiegrota nesošā kārta 60mm","m2",47.7,null,null,0,null,0,0,0,0,0,0,0]
[42,null,"Java M200","m3",0.063]
[43,null,"Stiegru siets 3/3/200/200","m2",1.05]
[44,null," Linoleja grīdas segums pielīmēts visā plaknē","m2",47.7,null,null,0,null,0,0,0,0,0,0,0]
[45,null,"Linolejs 34; 43 klase","m2",1.05]
[46,null,"Linoleja līme","l",0.25]
[47,null,"Kājlīstes","m",1.25]
[48,null,"5. Griesti."]
[49,null,"Veco griestu virsmu sagatavošana krāsošanai (tīrīšana, špaktelēšana, slīpēšana)","m²",47.7,null,null,0,null,0,0,0,0,0,0,0]
[50,null,"Špaktele Caparol Glattchtel","m²",1.03]
[51,null,"Griestu virsmas krāsošanas darbi","100m²",0.5,null,null,0,null,0,0,0,0,0,0,0]
[52,null,"Grunts Uni primer","l",12.5]
[53,null,"Krāsa griestiem","l",25]
[54,null,"5. Elektromontāža"]
[55,null,"Mainīt virsapmetuma lampas","gb.",12,null,null,0,null,0,0,0,0,0,0,0]
[56,null,"Dienas gaismas lampas","gb.",1]
[57,null,"Slēdžu, kontaktu montāža","gb.",5,null,null,0,null,0,0,0,0,0,0,0]
[58,null,"Slēdži, kontakti","gb.",1]
[59,null,"Kabeļu montāža iefrēzējot","m",94,null,null,0,null,0,0,0,0,0,0,0]
[60,null,"kabelis","m",1.03]
[61,null,"Ugunsdzēsības signalizācijas iekonservēšana, atjaunošana","c/st",4,null,null,0,null,0,0,0,0,0,0,0]
[{"$nulls":11},0,0,0,0,0]
[]
[{"$nulls":9},"Tiešās izmaksas:","Ls.",0,0,0,0,0]

{"sheet":"2","index":3,"n_rows":63,"n_cols":17,"rows_kept":63,"cut":false,"hidden":false,"merged":[[60,0,60,4],[0,0,0,15],[1,0,1,15],[8,11,8,12],[6,11,6,12],[7,11,7,12],[8,0,8,2],[9,7,9,10],[9,16,12,16],[10,7,10,10],[9,12,9,15],[10,12,10,15]],"flags":["formulas_cached_only"]}
["Lokālā tāme Nr. 2"]
["Remonta darbi telpā Nr.4 (dežuranta ofiss, pirms tam kambaris pie dziedāšanas klases)",{"$nulls":15},"Remonta darbi telpā Nr.4 (dežuranta ofiss, pirms tam kambaris pie dziedāšanas klases)"]
["Būves nosaukums:",null,"Kolkas pamatskola"]
["Objekta nosaukums:",null,"Kolkas pamatskolas 1. stāva remonts"]
["Objekta adrese:",null,"Kolkas pamatskola, Kolka, Kolkas pagasts, Dundagas novads, LV - 3275"]
["Pasūtījuma Nr.",null,"Dundagas novada pašvaldība"]
[{"$nulls":10},"Cilvēkstundas: ",0]
[{"$nulls":10},"Tāme sastādīta:",0]
[{"$nulls":10},"Tiešās izmaksas:",0]
[{"$nulls":7},"Vienības izmaksa",{"$nulls":4},"Kopējās izmaksas"]
["Nr.","Normat.","Darba un izdevumu nosaukums","Vienība","Daudz.","Laika","Darba ","tai skaitā",null,null,null,"Darba","tai skaitā"]
["p.","pozic.","pielietotie materiāli, to daudzums",null,null,"norma","samaksa","Darba alga","Materiāli","Mehanismi","Kopā","ietilpība","Darba alga","Materiāli","Mehanismi","Kopā"]
["k.","nr.",null,null,null,"C/st","Ls","Ls","Ls","Ls","Ls","C/st","Ls","Ls","Ls","Ls"]
[1,2,3,4,5,6,7,"8","9","10","11","12","13","14","15","16"]
[1,null,"1. Demontāžas darbi"]
[2,null," Iekšdurvju demontāžas darbi","gab.",1,null,null,0,null,0,0,0,0,0,0,0]
[3,null,"Grīdas seguma  demontāža ","m2",3.1,null,null,0,null,0,0,0,0,0,0,0]
[4,null,"Grīdas seguma konstrukcijas demontāža","m2",3.1,null,null,0,null,0,0,0,0,0,0,0]
[5,null,"Būvgružu nodošana izgāztuvē","t",0.2,null,null,0,null,0,0,0,0,0,0,0]
[6,null,"2. Sienas."]
[7,null,"Riģipša virsmu sagatavošana krāsošanai","m²",12.4,null,null,0,null,0,0,0,0,0,0,0]
[8,null,"Šuvju lenta","m",1.58]
[9,null,"Špaktele Knuaf Uniflot","kg",5.28]
[10,null,"Veco sienu virsmu sagatavošana krāsošanai (tīrīšana, špaktelēšana, slīpēšana)","m²",11.25,null,null,0,null,0,0,0,0,0,0,0]
[11,null,"Špaktele Caparol Glattchtel","m²",1.03]
[12,null,"Sienu virsmu krāsošanas darbi","100m²",0.24,null,null,0,null,0,0,0,0,0,0,0]
[13,null,"Grunts Uni primer","l",12.5]
[14,null,"Krāsa sienām tonēta","l",25]
[15,null,"3. Ailu aizpildījums."]
[16,null,"PVC divviru durvju bloka montāža","gab.",1,null,null,0,null,0,0,0,0,0,0,0]
[17,null,"PVC durvju bloks 2000x2100","gab.",1]
[18,null,"Montāžas putas","bal",1]
[19,null,"Skrūves, dībeļi","kpl",6]
[20,null,"Stiprinājumi","gab.",6]
[21,null,"4. Grīdas."]
[22,null,"Vājbetona sagatavošanas kārta b=100mm","m³",0.31,null,null,0,null,0,0,0,0,0,0,0]
[23,null,"Betons B5","m3",1.05]
[24,null,"Grīdas siltumizolācija b=100mm 1.stāva grīdām","m2",3.1,null,null,0,null,0,0,0,0,0,0,0]
[25,null,"Tenapors EPS100 100mm","m²",1.02]
[26,null," Javas M200 stiegrota nesošā kārta 60mm","m2",3.1,null,null,0,null,0,0,0,0,0,0,0]
[27,null,"Java M200","m3",0.063]
[28,null,"Stiegru siets 3/3/200/200","m2",1.05]
[29,null," Linoleja grīdas segums pielīmēts visā plaknē","m2",3.1,null,null,0,null,0,0,0,0,0,0,0]
[30,null,"Linolejs 34; 43 klase","m2",1.05]
[31,null,"Linoleja līme","l",0.25]
[32,null,"Kājlīstes","m",1.25]
[33,null,"5. Griesti."]
[34,null,"Veco griestu virsmu sagatavošana krāsošanai (tīrīšana, špaktelēšana, slīpēšana)","m²",3.1,null,null,0,null,0,0,0,0,0,0,0]
[35,null,"Špaktele Caparol Glattchtel","m²",1.03]
[36,null,"Griestu virsmas krāsošanas darbi","100m²",0.03,null,null,0,null,0,0,0,0,0,0,0]
[37,null,"Grunts Uni primer","l",12.5]
[38,null,"Krāsa griestiem","l",25]
[39,null,"5. Elektromontāža"]
[40,null,"Mainīt virsapmetuma lampas","gb.",1,null,null,0,null,0,0,0,0,0,0,0]
[41,null,"Dienas gaismas lampas","gb.",1]
[42,null,"Slēdžu, kontaktu montāža","gb.",2,null,null,0,null,0,0,0,0,0,0,0]
[43,null,"Slēdži, kontakti","gb.",1]
[44,null,"Kabeļu montāža iefrēzējot","m",20,null,null,0,null,0,0,0,0,0,0,0]
[45,null,"kabelis","m",1.03]
[46,null,"Ugunsdzēsības signalizācijas iekonservēšana, atjaunošana","c/st",1,null,null,0,null,0,0,0,0,0,0,0]
[{"$nulls":11},0,0,0,0,0]
[]
[{"$nulls":9},"Tiešās izmaksas:","Ls.",0,0,0,0,0]

{"sheet":"3","index":4,"n_rows":79,"n_cols":17,"rows_kept":79,"cut":false,"hidden":false,"merged":[[0,0,0,15],[1,0,1,15],[8,11,8,12],[6,11,6,12],[7,11,7,12],[8,0,8,2],[9,16,12,16],[9,7,9,10],[10,7,10,10],[76,0,76,4],[9,12,9,15],[10,12,10,15]],"flags":["formulas_cached_only"]}
["Lokālā tāme Nr. 3"]
["Gaiteņa un garderobes nodalījumu remonts",{"$nulls":15},"Gaiteņa un garderobes nodalījumu remonts"]
["Būves nosaukums:",null,"Kolkas pamatskola"]
["Objekta nosaukums:",null,"Kolkas pamatskolas 1. stāva remonts"]
["Objekta adrese:",null,"Kolkas pamatskola, Kolka, Kolkas pagasts, Dundagas novads, LV - 3275"]
["Pasūtījuma Nr.",null,"Dundagas novada pašvaldība"]
[{"$nulls":10},"Cilvēkstundas: ",0]
[{"$nulls":10},"Tāme sastādīta:",0]
[{"$nulls":10},"Tiešās izmaksas:",0]
[{"$nulls":7},"Vienības izmaksa",{"$nulls":4},"Kopējās izmaksas"]
["Nr.","Normat.","Darba un izdevumu nosaukums","Vienība","Daudz.","Laika","Darba ","tai skaitā",null,null,null,"Darba","tai skaitā"]
["p.","pozic.","pielietotie materiāli, to daudzums",null,null,"norma","samaksa","Darba alga","Materiāli","Mehanismi","Kopā","ietilpība","Darba alga","Materiāli","Mehanismi","Kopā"]
["k.","nr.",null,null,null,"C/st","Ls","Ls","Ls","Ls","Ls","C/st","Ls","Ls","Ls","Ls"]
[1,2,3,4,5,6,7,"8","9","10","11","12","13","14","15","16"]
[null,null,"1. Demontāžas darbi"]
[1,null," Iekšdurvju demontāžas darbi","gab.",5,null,null,0,null,0,0,0,0,0,0,0]
[2,null,"Grīdas seguma  demontāža ","m2",118.1,null,null,0,null,0,0,0,0,0,0,0]
[3,null,"Grīdas seguma konstrukcijas demontāža","m2",118.1,null,null,0,null,0,0,0,0,0,0,0]
[4,null,"Būvgružu nodošana izgāztuvē","t",7.7,null,null,0,null,0,0,0,0,0,0,0]
[5,null,"2. Sienas."]
[6,null,"Starpsienu metāla karkasa iebūve W112(100) riģipša plātne 2 kārtās","m²",7.9,null,null,0,null,0,0,0,0,0,0,0]
[7,null,"UW profils 100x40x06","m",0.74]
[8,null,"CW profils 100x50x06","m",2.06]
[9,null,"Dībelis K6/35","gb.",1.65]
[10,null,"Izolācijas plāksne Paroc UNS 100mm","m²",1.02]
[11,null,"Riģipša plāksne GKB","m²",4.1]
[12,null,"Riģipša skrūves TN25","100gb",0.132]
[13,null,"Riģipša skrūves TN35","100gb",0.295]
[14,null,"Riģipša virsmu sagatavošana krāsošanai","m²",15.8,null,null,0,null,0,0,0,0,0,0,0]
[15,null,"Šuvju lenta","m",1.58]
[16,null,"Špaktele Knuaf Uniflot","kg",5.28]
[17,null,"Veco sienu virsmu sagatavošana krāsošanai (tīrīšana, špaktelēšana, slīpēšana)","m²",356.2,null,null,0,null,0,0,0,0,0,0,0]
[18,null,"Špaktele Caparol Glattchtel","m²",1.03]
[19,null,"Sienu virsmu krāsošanas darbi","100m²",3.72,null,null,0,null,0,0,0,0,0,0,0]
[20,null,"Grunts Uni primer","l",12.5]
[21,null,"Krāsa sienām tonēta","l",25]
[22,null,"Iestrādāt sietu riģipša sienās ventilācijai","m²",0.3,null,null,0,null,0,0,0,0,0,0,0]
[23,null,"smalka metālisks siets","m²",1.03]
[24,null,"3. Ailu aizpildījums."]
[25,null,"Iekšdurvju, koka 80x209cm iebūve","gab.",5,null,null,0,null,0,0,0,0,0,0,0]
[26,null,"Iekšdurvju bloks ar restīti ventilācijai","gab.",1]
[27,null,"Montāžas putas","balons",0.3]
[28,null,"Rokturi","gab.",1]
[29,null,"Seglīstes","m",5.6]
[30,null,"Skrūves, dībeļi","gab.",6]
[31,null,"Stiprinājumi","gab.",6]
[32,null,"Garderobes karināmie","kpl",4,null,null,0,null,0,0,0,0,0,0,0]
[33,null,"Drēbju karināmie","kpl",1]
[34,null,"Plauktu sistēmas montāža","kpl",1,null,null,0,null,0,0,0,0,0,0,0]
[35,null,"Plaukti","kpl",1]
[36,null,"4. Grīdas."]
[37,null,"Vājbetona sagatavošanas kārta b=100mm","m³",12.23,null,null,0,null,0,0,0,0,0,0,0]
[38,null,"Betons B5","m3",1.05]
[39,null,"Grīdas siltumizolācija b=100mm 1.stāva grīdām","m2",122.3,null,null,0,null,0,0,0,0,0,0,0]
[40,null,"Tenapors EPS100 100mm","m²",1.02]
[41,null," Javas M200 stiegrota nesošā kārta 60mm","m2",122.3,null,null,0,null,0,0,0,0,0,0,0]
[42,null,"Java M200","m3",0.063]
[43,null,"Stiegru siets 3/3/200/200","m2",1.05]
[44,null," Linoleja grīdas segums pielīmēts visā plaknē","m2",122.3,null,null,0,null,0,0,0,0,0,0,0]
[45,null,"Linolejs 34; 43 klase","m2",1.05]
[46,null,"Linoleja līme","l",0.25]
[47,null,"Kājlīstes","m",1.25]
[48,null,"5. Griesti."]
[49,null,"Veco griestu virsmu sagatavošana krāsošanai (tīrīšana, špaktelēšana, slīpēšana) k=1.3","m²",159,null,null,0,null,0,0,0,0,0,0,0]
[50,null,"Špaktele Caparol Glattchtel","m²",1.03]
[51,null,"Griestu virsmas krāsošanas darbi","100m²",1.59,null,null,0,null,0,0,0,0,0,0,0]
[52,null,"Grunts Uni primer","l",12.5]
[53,null,"Krāsa griestiem","l",25]
[54,null,"5. Elektromontāža"]
[55,null,"Mainīt virsapmetuma lampas","gb.",22,null,null,0,null,0,0,0,0,0,0,0]
[56,null,"Dienas gaismas lampas","gb.",1]
[57,null,"Slēdžu, kontaktu montāža","gb.",11,null,null,0,null,0,0,0,0,0,0,0]
[58,null,"Slēdži, kontakti","gb.",1]
[59,null,"Kabeļu montāža iefrēzējot","m",165,null,null,0,null,0,0,0,0,0,0,0]
[60,null,"kabelis","m",1.03]
[61,null,"Ugunsdzēsības signalizācijas iekonservēšana, atjaunošana","c/st",8,null,null,0,null,0,0,0,0,0,0,0]
[{"$nulls":11},0,0,0,0,0]
[]
[{"$nulls":9},"Tiešās izmaksas:","Ls.",0,0,0,0,0]

{"sheet":"4","index":5,"n_rows":55,"n_cols":17,"rows_kept":55,"cut":false,"hidden":false,"merged":[[9,16,12,16],[9,7,9,10],[9,12,9,15],[10,12,10,15],[52,0,52,4],[0,0,0,15],[1,0,1,15],[8,11,8,12],[6,11,6,12],[7,11,7,12],[8,0,8,2],[10,7,10,10]],"flags":["formulas_cached_only"]}
["Lokālā tāme Nr. 4"]
["Durvju maiņa gaitenī",{"$nulls":15},"Durvju maiņa gaitenī"]
["Būves nosaukums:",null,"Kolkas pamatskola"]
["Objekta nosaukums:",null,"Kolkas pamatskolas 1. stāva remonts"]
["Objekta adrese:",null,"Kolkas pamatskola, Kolka, Kolkas pagasts, Dundagas novads, LV - 3275"]
["Pasūtījuma Nr.",null,"Dundagas novada pašvaldība"]
[{"$nulls":10},"Cilvēkstundas: ",0]
[{"$nulls":10},"Tāme sastādīta:",0]
[{"$nulls":10},"Tiešās izmaksas:",0]
[{"$nulls":7},"Vienības izmaksa",{"$nulls":4},"Kopējās izmaksas"]
["Nr.","Normat.","Darba un izdevumu nosaukums","Vienība","Daudz.","Laika","Darba ","tai skaitā",null,null,null,"Darba","tai skaitā"]
["p.","pozic.","pielietotie materiāli, to daudzums",null,null,"norma","samaksa","Darba alga","Materiāli","Mehanismi","Kopā","ietilpība","Darba alga","Materiāli","Mehanismi","Kopā"]
["k.","nr.",null,null,null,"C/st","Ls","Ls","Ls","Ls","Ls","C/st","Ls","Ls","Ls","Ls"]
[1,2,3,4,5,6,7,"8","9","10","11","12","13","14","15","16"]
[null,null,"1. Demontāžas darbi"]
[1,null," Iekšdurvju demontāžas darbi","gab.",3,null,null,0,null,0,0,0,0,0,0,0]
[2,null,"Stiklotu sieniņu montāža pie durvīm","m2",8.9,null,null,0,null,0,0,0,0,0,0,0]
[3,null,"Būvgružu nodošana izgāztuvē","t",0.2,null,null,0,null,0,0,0,0,0,0,0]
[4,null,"2. Sienas."]
[5,null,"Ugunsdrošas starpsienas montāža","m²",8.9,null,null,0,null,0,0,0,0,0,0,0]
[6,null,"UW profils 50x40x06","m",0.74]
[7,null,"CW profils 50x50x06","m",2.06]
[8,null,"Dībelis K6/35","gb.",1.65]
[9,null,"Izolācijas plāksne Paroc UNS 50mm","m²",1.02]
[10,null,"Riģipša plāksne ugunsdroša GKF","m²",4.1]
[11,null,"Riģipša skrūves TN25","100gb",0.132]
[12,null,"Riģipša skrūves TN35","100gb",0.295]
[13,null,"Riģipša virsmu sagatavošana krāsošanai","m²",17.8,null,null,0,null,0,0,0,0,0,0,0]
[14,null,"Šuvju lenta","m",1.58]
[15,null,"Špaktele Knuaf Uniflot","kg",5.28]
[16,null,"Sienu virsmu krāsošanas darbi","100m²",0.18,null,null,0,null,0,0,0,0,0,0,0]
[17,null,"Grunts Uni primer","l",12.5]
[18,null,"Krāsa sienām tonēta","l",25]
[19,null,"Aiļu virsmu sagatavošana krāsošanai (tīrīšana, špaktelēšana, slīpēšana)","m²",5.5,null,null,0,null,0,0,0,0,0,0,0]
[20,null,"Špaktele Caparol Glattchtel","m²",1.03]
[21,null,"Špaktele Knuaf Uniflot","kg",5.28]
[22,null,"Aiļu virsmu krāsošanas darbi","100m²",0.055,null,null,0,null,0,0,0,0,0,0,0]
[23,null,"Grunts Uni primer","l",12.5]
[24,null,"Krāsa sienām tonēta","l",25]
[25,null,"3. Ailu aizpildījums."]
[26,null,"Udunsdrošu bloku montāža ","gab.",2,null,null,0,null,0,0,0,0,0,0,0]
[27,null,"Ugunsdrošs durvju bloks ar aizvērēju","gab.",1]
[28,null,"Montāžas putas","bal",1]
[29,null,"Skrūves, dībeļi","kpl",6]
[30,null,"Stiprinājumi","gab.",6]
[31,null,"PVC divviru durvju bloka montāža","gab.",1,null,null,0,null,0,0,0,0,0,0,0]
[32,null,"PVC divviru durvju bloka montāža","gab.",1]
[33,null,"Montāžas putas","balons",0.3]
[34,null,"Rokturi","gab.",1]
[35,null,"Seglīstes","m",5.6]
[36,null,"Skrūves, dībeļi","gab.",6]
[37,null,"Stiprinājumi","gab.",6]
[{"$nulls":11},0,0,0,0,0]
[]
[{"$nulls":9},"Tiešās izmaksas:","Ls.",0,0,0,0,0]

{"sheet":"5","index":6,"n_rows":24,"n_cols":17,"rows_kept":24,"cut":false,"hidden":false,"merged":[[9,16,12,16],[9,7,9,10],[9,12,9,15],[10,12,10,15],[21,0,21,4],[0,0,0,15],[1,0,1,15],[8,11,8,12],[6,11,6,12],[7,11,7,12],[8,0,8,2],[10,7,10,10]],"flags":["formulas_cached_only"]}
["Lokālā tāme Nr. 5"]
["Santehnikas darbi",{"$nulls":15},"Santehnikas darbi"]
["Būves nosaukums:",null,"Kolkas pamatskola"]
["Objekta nosaukums:",null,"Kolkas pamatskolas 1. stāva remonts"]
["Objekta adrese:",null,"Kolkas pamatskola, Kolka, Kolkas pagasts, Dundagas novads, LV - 3275"]
["Pasūtījuma Nr.",null,"Dundagas novada pašvaldība"]
[{"$nulls":10},"Cilvēkstundas: ",0]
[{"$nulls":10},"Tāme sastādīta:",0]
[{"$nulls":10},"Tiešās izmaksas:",0]
[{"$nulls":7},"Vienības izmaksa",{"$nulls":4},"Kopējās izmaksas"]
["Nr.","Normat.","Darba un izdevumu nosaukums","Vienība","Daudz.","Laika","Darba ","tai skaitā",null,null,null,"Darba","tai skaitā"]
["p.","pozic.","pielietotie materiāli, to daudzums",null,null,"norma","samaksa","Darba alga","Materiāli","Mehanismi","Kopā","ietilpība","Darba alga","Materiāli","Mehanismi","Kopā"]
["k.","nr.",null,null,null,"C/st","Ls","Ls","Ls","Ls","Ls","C/st","Ls","Ls","Ls","Ls"]
[1,2,3,4,5,6,7,"8","9","10","11","12","13","14","15","16"]
[null,null,"1. Ūdensvads"]
[1,null,"Daudzslāņu caurule d16","m",8,null,null,0,null,0,0,0,0,0,0,0]
[2,null,"Daudzslāņu fasondaļas","kompl",1,null,null,0,null,0,0,0,0,0,0,0]
[3,null,"Siltum izolācijas čaula","m",8,null,null,0,null,0,0,0,0,0,0,0]
[4,null,"2. Kanalizācijas vads"]
[5,null,"Kanalizācijas caurule ar veidgabaliem ","m",32,null,null,0,null,0,0,0,0,0,0,0]
[6,null,"Palīgmateriāli","k-ts",1,null,null,0,null,0,0,0,0,0,0,0]
[{"$nulls":11},0,0,0,0,0]
[]
[{"$nulls":9},"Tiešās izmaksas:","Ls.",0,0,0,0,0]